## Sheet1
This file is only meant to assist with traceability of user stories and backlog items. Our github repository demonstrates traceability through pull requests which have linked backlog items which have, mostly, been derived from user stories
User Story | Action Number | Completion Criteria |  |  | PULL REQUEST
An an application user I want the software to warn the user deletion is irreversible | #64 | Backlog items #20 and #21 are completed |  |  | #47
As an application user I want the screen to show me that i have no tasks when there are no tasks rather than be blank | #48 | Backlog item #49 completed |  |  | #56
As an application user I want to be notified when I have To-Do items that have not been completed so I do not forget about them | #46 | Backlog items #12, #14, #17, and #18 completed
As an application user I want to be able to delete To-Do items so I can free up space on my device. | #45 | Backlog item #8 Is completed |  |  | #47
As an application user I want to be able to modify the font size within the application so I can better see the text. | #43 | Backlog item #13 completed |  |  | #81
As an application user I want to be able to create copies of an existing To-Do item so I can create tasks identical to an existing task faster. | #36 | Backlog item #23
As an application user I want to be able to modify existing To-Do items so I can change the details or dates relating to the task without having to delete it and create a new one. | #33 | Backlog #84 completed |  |  | #87
As an application user I want my To-Do items to be stored so I can close and reopen the application and my items will still be there. | #31 | Backlog item #5 Completed |  |  | #26
As an application user I want to be able to mark To-Do items as completed so I can keep track of which To-Do items have been finished. | #30 | Backlog item #7 and #59 completed |  |  | #60
As an application user I want to be able to add items to my list of existing items so I can make new To-Do items. | #28 | Backlog item #4, #9, #10, #18, #50-#52, #76-78 completed
As an application user I want a task to store related details and dates so I can better remember the task I have created. | #27 | Backlog item #22 completed |  |  | #24
Backlog Item | Action Number | Linked User Story | Verification Method | Completion Criteria
The user shall be able to edit an existing task | #84 | #33 | Test | EditTaskTest() in HomeFragmentInstrumentedTest.java | #87
The RecyclerView shall be sorted by the due date of the tasks | #82 |  | Test |  | #83
Upon clicking create task, all user data entered in Add Task Pop-up Window should get stored to local database. | #78 | #28 | Test
Upon clicking the cancel button no data should be saved to database. | #77 | #28 | Test
Fixing the due date field: Detect Current year and Minimum due date year should be current year and maximum due date year should next year. | #76 | #28 | Test
code clean up | #75 |  | Inspection | Other group members review and approve code
Notification button should be functional to allow user to create a notification | #72 | #46 | Test
Create a notification option button in new task template | #71 | #46 | Test
Make splash screen when app is opened | #70 |  | Demonstrate | Run app, verify new splash screen is used when app opened
Change app icon on home screen so that looks like a ToDo list app | #69 |  | Demonstrate | Open emulator and verify app icon is not the default icon | #80
The software shall find available primary key values for use with new tasks. | #68 | #28 | Test |  | #79
Disable EditText of Today's Date when it gains focus and will remain grey throughout creating task | #65 | #28 | Test |  | #66
The floating Add Item Button (floating action button) should hide when the Add Task pop up window opens and appear when we are on the main screen | #63 | #28 | Test
Recycler list shall have utilize card view for a better UI experience | #62 |  | Demonstrate | Run app, verify new appearance for task containers exists | #61
The software shall have a 'completed' Fragment to display tasks marked as complete | #59 | #30 | Test | All tests in CompletedFragmentInstrumentedTest.java | #60
Bug Test: Main branch broken | #53 |  | Demonstrate | When app is run there are No runtime errors | #54
create all text fields in pop-up window supporting different text fields/functionalities | #52 | #28 | Test |  | #57
Make "Create Task" button inside pop-up window | #51 | #28 | Test |  | #57
pop-up window should successfully open upon clicking add button | #50 | #28 | Test | testFabPerformClick() in MainActivityTest.java passes | #57
The HomeFragment shall display a textView rather than recyclerView when there are no tasks | #49 | #48 | Test | emptyQueryTextViewTest() in HomeFragmentInstrumentedTest.java | #56
Cancel button should allow user to be able to cancel out of the add task pop-up window that will bring them back to the main page | #40 | #28 | Test |  | #74
The software shall allow the user to select existing tasks from the list | #37 |  | Test | clickRecyclerViewItemTest() in HomeFragmentInstrumentedTest.java | #38
The user shall be able to make copies of tasks/items | #23 | #36 | Test
Create Task class | #22 | #27 | Test | All tests in TaskTest.java | #24
The task Deletion Pop-up (Issue #20) shall be functional | #21 | #64 | Test | cancelDeleteTest() and confirmDeleteTest() in HomeFragmentInstrumentedTest.java | #47
The software shall have a task Deletion Pop-up (Are you Sure? (Confirm/Cancel)) | #20 | #64 | Test | clickBottomSheetDeleteTest() in HomeFragmentInstrumentedTest.java | #47
The AddModifyTask View (Issue #18) shall be functional | #19 | #28 | Test
The software shall have a layout/view for Adding task | #18 | #28 | Test | testFabPerformClick() in MainActivityTest.java | #57
The user shall be able to modify the notification message | #17 | #46 | Test
The user shall be able to specify date and time frequency | #16 | #46 | Test
The software shall use a database to store data | #15 | #31 | Test | All tests in AppDatabaseTest.java | #26
Create android alarm for task item | #14 | #46 | Test |  | #55
The software shall allow the user to change default font size. | #13 | #43 | Test |  | #81
The software shall implement push notifications for To Do item | #12 | #46 | Test |  | #55
Choose different theme | #11 |  | Demonstrate | On app launch, theme is different from defaults | #55
The software shall implement today's date by default | #10 | #28 | Test |  | #57
The software shall implement due date for to do items | #9 | #28 | Test |  | #73
The software shall implement ability to Delete task/item | #8 | #45 | Test | confirmDeleteTest() in HomeFragmentInstrumentedTest.java | #47
The software shall allow user to mark task/items as completed | #7 | #30 | Test | MarkCompleteTest() in HomeFragmentInstrumentedTest.java | #60
Change current template icons and names | #6 |  | Demonstrate | Running app now shows custom art instead of default | #80
The software shall locally store data on phone | #5 | #31 | Test | All tests in AppDatabaseTest.java | #26
The software shall implement add button to add items onto list | #4 | #28 | Test | testFabPerformClick() in MainActivityTest.java | #41
Learn Android studio UI design | #3 |  | Demonstrate | Demonstrated through development progress | N/A
Create UI list to show To Do items | #2 |  | Test | populatedQueryRecyclerViewTest() in HomeFragmentInstrumentedTest.java | #25