# Date:

3/23/2023

# Time:

12:00PM

# Attendees/Role:

Jay (Scrum Master/Product owner) – online ,

Bruce (Team Member/Product owner),

Marwa (Team Member/Product owner),

Austin (Team Member/Product owner),

Alyana (Team Member/Product owner)

# Project Title:

To Do List

Previous Action Items Completed (GitHub Issues):

* Project Overview and SDP
* Continue work on/learning Android Studio
* Create personal branch
* #2 UI list to show To Do items created
* #22 Create task class
* #5 Software shall locally store data on phone
* Finalized SDP
* Issues with Android Studio and progress with learning it.
* #37 To Do List items are interactive
* #4 implement add button
* #53 Bug Test: Main branch broken
* #8 software shall implement ability to delete task/item
* #20 software shall have a task deletion pop up
* #21 task deletion pop-up shall be functional
* #49 HomeFragment shall display a textView rather than rcyclerView when there are no tasks
* Deciding user stories – dividing them up (for two each)

# Items Discussed *(Decisions made)*:

* Progress on current tasks.
* All go through review tasks to approve them (#12, #14, #11, #4)
* Continue work
* Pull requests need to be reviewed
* Fill out check sheet for future
* Doxygen

Action Items (GitHub Issues):

* Continue work on individual tasks/issues
* Do pull requests
* #50 pop-up window should successfully open upon clicking add button
* #23 user shall be able to make copies of tasks/items
* #7 software shall allow user to mark task/items as completed
* #17 user shall be able to modify the notification message
* #16 user shall be able to specify date and time frequency (i.e. every Wednesday)

# (Agile) Project Sprint 3 Scrum 2:

The following identifies the estimate of items to be worked in each sprint.

* + 1/30/2023 Sprint 0 (Pre-sprint setup)
    - Set plan (Completed)
    - Learn Android Studio (Completed)
    - Set up GitHub (Completed)
  + 2/13/2023 Sprint 1
    - Everyone shall create their own branch (Completed)
    - Setup development environment (Completed)
    - Setup GitHub for Version Control (Completed)

▪ #3 Learn Android Studio (work in prog - continuous)

* + - #2 Develop UI List to display task items (Completed)
    - #22 Create Task Class (Completed)
  + 2/27/2023 Sprint 2 (Spring Break Included)
    - #37 Select existing tasks from list (Completed)
    - #5 Save list items locally to android device (Completed)
    - #53 Bug Test: Main Branch Broken (Completed)

o 3/13/2023 Sprint 3

* + - #4 Integrate button to allow for adding items (Completed)
    - #12 Send Android notification for task items (in review)
    - #20 Design DeletionConfirmation Pop-up View (Completed)
    - #21 The task deletion pop-up(#20) is functional (Completed)
    - #8 Integrate deleting task items from UI list (Completed)
    - #11 Choose different Theme (in progress)
    - #49 The HomeFragment displays a textView rather than recyclerView when there are no tasks (Completed)
    - #23 user shall be able to make copies of tasks/items (in progress)

o 3/27/2023 Sprint 4

* + - #7 software shall allow user to mark task/items as completed (in progress)
    - #17 user shall be able to modify the notification message (in progress)
    - #62 Recycler list shall utilize card view for a better UI experience
    - #18 Layout/view for Adding Task
    - #14 Create android alarm for task item
    - #13 The software shall allow user to change font-size
    - #68 software shall find available primary key values
    - #69 Change app icon on home screen
    - #65 Disable editText of today’s Date when it gains focus (NEW)
    - #9 implement due date for to do items (NEW)
    - #51 Make “create task button (NEW)
    - #10 Implement Today’s Date by default (NEW)
    - #59 Software shall have ‘completed’ fragment to display completed tasks (NEW)
    - #40 cancel button shall remove ‘add task’ pop-up (NEW)
    - #77 When cancel is hit, no data is saved (NEW)

o 4/10/2023 Sprint 5

* + - #16 Create Scheduling for Task items